## Risk Register
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status | Probability Score | Impact Score | Risk Score
R03 | 1 | Competitor apps | Platforms like PetBacker and Pawshake already exist with market share | Competitors (Business) | Strong existing competitors with more features and funding | Users trust and prefer existing apps | Mitigate: Focus on niche differentiation, local market focus | Chloie | Likely | Major | Open | 4 | 4 | 16
R08 | 1 | Critical software bugs | Defects break major flows or data | Software (Technical) | Inadequate testing | Crashes or major bugs | Mitigate: Unit and integration tests, peer reviews, bug tracking | Zi Jian | Likely | Major | In Progress | 4 | 4 | 16
R25 | 1 | Scope Creep | Uncontrolled scope growth mid-sprint | Scope Creep (Project Management) | Weak change control | Adhoc feature requests | Mitigate: Apply change request approval process | Quang | Likely | Major | Open | 4 | 4 | 16
R01 | 4 | Low adoption due to poor usability | Users may not use the app if onboarding or navigation is confusing | Customer Adoption (Business) | Weak UI/UX design, no usability testing conducted | Drop-off during sign up, low retention | Mitigate: Conduct usability testing, simplify onboarding, gather feedback | Zi Jian | Likely | Moderate | Open | 4 | 3 | 12
R04 | 4 | Limited budget for tools | Budget limits restrict paid APIs or hosting services needed for final delivery | Cash Flow (Business) | Insufficient funds | Blocked access to tools | Mitigate: Use open-source tools and student licenses | Quang | Likely | Moderate | Monitoring | 4 | 3 | 12
R07 | 4 | Deployment environment failure | Hosting/misconfiguration will cause downtime near demo/submission | Hardware (Technical) | Misconfigured pipeline/host | Unavailable app | Mitigate: Conduct early deployment tests and maintain working backups | Anthony | Possible | Major | In Progress | 3 | 4 | 12
R11 | 4 | API integration failure | Incorrect endpoints or API calls or data handling will cause errors between modules | Integration (Technical) | Mismatched interfaces | Broken screens | Mitigate: Conduct API integration tests with mock data | Quang | Possible | Major | Open | 3 | 4 | 12
R16 | 4 | Lack of requirement validation | Wrong/partial features delivered/built in final product | User Support (Organizational) | Skipped validation | Rework and low satisfaction | Mitigate: Validate requirements with stakeholder during lab sessions | Athena | Likely | Moderate | Open | 4 | 3 | 12
R17 | 4 | Imbalanced workload | Some members may be overloaded with work causing burnouts and delays in delivery | Team Support (Organizational) | Poor task allocation | Missed tasks | Mitigate: Track workloads, redistribute tasks accordingly | Chloie | Likely | Moderate | In Progress | 4 | 3 | 12
R20 | 4 | Underestimation of effort | Tasks taking longer than planned | Estimates (Project Management) | Optimistic estimates | Sprint spillover | Mitigate: Re-estimate based on past sprints, add buffer for more critical tasks | Nelly | Likely | Moderate | Monitoring | 4 | 3 | 12
R23 | 4 | Overlapping module deadlines | Bottlenecks create merge/integration difficulties | Schedule (Project Management) | Poor sequencing | Merge conflicts | Mitigate: Stagger deadlines, use Gantt for schedule tracking | Athena | Likely | Moderate | Monitoring | 4 | 3 | 12
R24 | 4 | Missed lab submission deadlines | Overload or slippage leading to late submission | Schedule (Project Management) | Tight timeline | Last-minute work | Mitigate: Set internal deadlines earlier than official submission dates | Chloie | Possible | Major | Open | 3 | 4 | 12
R14 | 13 | Data privacy breach | Personal information exposed due to poor controls | Security (Technical) | Weak access control | Suspicious access | Mitigate: Apply encryption, restrict access permissions | Anthony | Unlikely | Catastrophic | Open | 2 | 5 | 10
R02 | 14 | Pet owners distrust providers | Lack of transparency and reviews may reduce trust in services offered | Customer Adoption (Business) | No credibility system for providers | Users does not want to book | Mitigate: Add existing reviews (i.e. From Google/Website), Add verified provider badges (optional) | Athena | Possible | Moderate | Open | 3 | 3 | 9
R09 | 14 | Dependency issues | Library conflicts or deprecated packages will break the application build | Software (Technical) | Unpinned/old dependencies | Build/CI failures | Mitigate: Lock dependency versions and test updates | Athena | Possible | Moderate | Monitoring | 3 | 3 | 9
R12 | 14 | Database schema mismatch | Frontend/backend misaligned with database schema changes | Integration (Technical) | Uncoordinated schema updates | Data load errors | Mitigate: Backend to sync with frontend upon any changes | Chong Yao | Possible | Moderate | Open | 3 | 3 | 9
R15 | 14 | Expectations misalignment | Stakeholders' goals not aligned with team deliverables | Executive Support (Organizational) | Communication gaps | Conflicting feedback | Mitigate: Ensure alignment suring weekly team meetings to confirm requirements | Zi Jian | Possible | Moderate | Open | 3 | 3 | 9
R18 | 14 | Conflicts/Miscommunication | Friction between members or unclear roles/communications will slow project progress | Team Support (Organizational) | Unclear roles and responsibilities | Duplicate/blocked work | Mitigate: Maintain open channels and use retrospectives | Quang | Possible | Moderate | Closed | 3 | 3 | 9
R21 | 14 | Missed updates or unclear requirements | Poor notes/follow-up causes rework | Communication (Project Management) | Weak documentation | Rework and team confusion | Mitigate: Maintain project logs and minutes | Anthony | Possible | Moderate | In Progress | 3 | 3 | 9
R22 | 14 | Limited access to tools | Potential account/license issues block progress | Resources (Project Management) | Expired accounts | Blocked commits/tests | Mitigate: Verify access early and renew subscriptions if any in advance | Zi Jian | Possible | Moderate | Open | 3 | 3 | 9
R05 | 21 | Google OAuth policy change | Auth may break if Google changes policies or scopes | Supplier (Business) | External provider dependency | Login failures post-change | Mitigate: Monitor API notices, implement email/password backup | Chong Yao | Unlikely | Major | Monitoring | 2 | 4 | 8
R10 | 22 | Poor internet connection | Unstable Wi-Fi/internet connection will cause slow/failed demo | Network (Technical) | Venue connectivity | Timeouts or consistent lag | Accept: Prepare offline demo video backup | Nelly | Possible | Minor | Open | 3 | 2 | 6
R13 | 22 | Weak password enforcement | Poor password rules might enable account compromise | Security (Technical) | Inadequate validation | Authentication anomalies | Mitigate: Enforce stronger password rules and add validation | Chloie | Unlikely | Moderate | Closed | 2 | 3 | 6
R19 | 22 | Member unavailable | Illness/emergency removes key team members contributions | Resource Availability (Organizational) | Single-point ownership | Missed deliverables | Mitigate: Assign secondary owners (Member from same team) | Chong Yao | Possible | Minor | Open | 3 | 2 | 6
R06 | 25 | Payment gateway fees | Higher/hidden fees increase project cost | Cash Flow (Business) | Fee structure changes | Cost overrun in tests | Transfer: Include buffer and display fees to users if needed | Nelly | Unlikely | Minor | Open | 2 | 2 | 4

## Unsorted Risk Register
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status | Probability Score | Impact Score | Risk Score
R01 | 4 | Low adoption due to poor usability | Users may not use the app if onboarding or navigation is confusing | Customer Adoption (Business) | Weak UI/UX design, no usability testing conducted | Drop-off during sign up, low retention | Mitigate: Conduct usability testing, simplify onboarding, gather feedback | Zi Jian | Likely | Moderate | Open | 4 | 3 | 12
R02 | 14 | Pet owners distrust providers | Lack of transparency and reviews may reduce trust in services offered | Customer Adoption (Business) | No credibility system for providers | Users does not want to book | Mitigate: Add existing reviews (i.e. From Google/Website), Add verified provider badges (optional) | Athena | Possible | Moderate | Open | 3 | 3 | 9
R03 | 1 | Competitor apps | Platforms like PetBacker and Pawshake already exist with market share | Competitors (Business) | Strong existing competitors with more features and funding | Users trust and prefer existing apps | Mitigate: Focus on niche differentiation, local market focus | Chloie | Likely | Major | Open | 4 | 4 | 16
R04 | 4 | Limited budget for tools | Budget limits restrict paid APIs or hosting services needed for final delivery | Cash Flow (Business) | Insufficient funds | Blocked access to tools | Mitigate: Use open-source tools and student licenses | Quang | Likely | Moderate | Monitoring | 4 | 3 | 12
R05 | 21 | Google OAuth policy change | Auth may break if Google changes policies or scopes | Supplier (Business) | External provider dependency | Login failures post-change | Mitigate: Monitor API notices, implement email/password backup | Chong Yao | Unlikely | Major | Monitoring | 2 | 4 | 8
R06 | 25 | Payment gateway fees | Higher/hidden fees increase project cost | Cash Flow (Business) | Fee structure changes | Cost overrun in tests | Transfer: Include buffer and display fees to users if needed | Nelly | Unlikely | Minor | Open | 2 | 2 | 4
R07 | 4 | Deployment environment failure | Hosting/misconfiguration will cause downtime near demo/submission | Hardware (Technical) | Misconfigured pipeline/host | Unavailable app | Mitigate: Conduct early deployment tests and maintain working backups | Anthony | Possible | Major | In Progress | 3 | 4 | 12
R08 | 1 | Critical software bugs | Defects break major flows or data | Software (Technical) | Inadequate testing | Crashes or major bugs | Mitigate: Unit and integration tests, peer reviews, bug tracking | Zi Jian | Likely | Major | In Progress | 4 | 4 | 16
R09 | 14 | Dependency issues | Library conflicts or deprecated packages will break the application build | Software (Technical) | Unpinned/old dependencies | Build/CI failures | Mitigate: Lock dependency versions and test updates | Athena | Possible | Moderate | Monitoring | 3 | 3 | 9
R10 | 22 | Poor internet connection | Unstable Wi-Fi/internet connection will cause slow/failed demo | Network (Technical) | Venue connectivity | Timeouts or consistent lag | Accept: Prepare offline demo video backup | Nelly | Possible | Minor | Open | 3 | 2 | 6
R11 | 4 | API integration failure | Incorrect endpoints or API calls or data handling will cause errors between modules | Integration (Technical) | Mismatched interfaces | Broken screens | Mitigate: Conduct API integration tests with mock data | Quang | Possible | Major | Open | 3 | 4 | 12
R12 | 14 | Database schema mismatch | Frontend/backend misaligned with database schema changes | Integration (Technical) | Uncoordinated schema updates | Data load errors | Mitigate: Backend to sync with frontend upon any changes | Chong Yao | Possible | Moderate | Open | 3 | 3 | 9
R13 | 22 | Weak password enforcement | Poor password rules might enable account compromise | Security (Technical) | Inadequate validation | Authentication anomalies | Mitigate: Enforce stronger password rules and add validation | Chloie | Unlikely | Moderate | Closed | 2 | 3 | 6
R14 | 13 | Data privacy breach | Personal information exposed due to poor controls | Security (Technical) | Weak access control | Suspicious access | Mitigate: Apply encryption, restrict access permissions | Anthony | Unlikely | Catastrophic | Open | 2 | 5 | 10
R15 | 14 | Expectations misalignment | Stakeholders' goals not aligned with team deliverables | Executive Support (Organizational) | Communication gaps | Conflicting feedback | Mitigate: Ensure alignment suring weekly team meetings to confirm requirements | Zi Jian | Possible | Moderate | Open | 3 | 3 | 9
R16 | 4 | Lack of requirement validation | Wrong/partial features delivered/built in final product | User Support (Organizational) | Skipped validation | Rework and low satisfaction | Mitigate: Validate requirements with stakeholder during lab sessions | Athena | Likely | Moderate | Open | 4 | 3 | 12
R17 | 4 | Imbalanced workload | Some members may be overloaded with work causing burnouts and delays in delivery | Team Support (Organizational) | Poor task allocation | Missed tasks | Mitigate: Track workloads, redistribute tasks accordingly | Chloie | Likely | Moderate | In Progress | 4 | 3 | 12
R18 | 14 | Conflicts/Miscommunication | Friction between members or unclear roles/communications will slow project progress | Team Support (Organizational) | Unclear roles and responsibilities | Duplicate/blocked work | Mitigate: Maintain open channels and use retrospectives | Quang | Possible | Moderate | Closed | 3 | 3 | 9
R19 | 22 | Member unavailable | Illness/emergency removes key team members contributions | Resource Availability (Organizational) | Single-point ownership | Missed deliverables | Mitigate: Assign secondary owners (Member from same team) | Chong Yao | Possible | Minor | Open | 3 | 2 | 6
R20 | 4 | Underestimation of effort | Tasks taking longer than planned | Estimates (Project Management) | Optimistic estimates | Sprint spillover | Mitigate: Re-estimate based on past sprints, add buffer for more critical tasks | Nelly | Likely | Moderate | Monitoring | 4 | 3 | 12
R21 | 14 | Missed updates or unclear requirements | Poor notes/follow-up causes rework | Communication (Project Management) | Weak documentation | Rework and team confusion | Mitigate: Maintain project logs and minutes | Anthony | Possible | Moderate | In Progress | 3 | 3 | 9
R22 | 14 | Limited access to tools | Potential account/license issues block progress | Resources (Project Management) | Expired accounts | Blocked commits/tests | Mitigate: Verify access early and renew subscriptions if any in advance | Zi Jian | Possible | Moderate | Open | 3 | 3 | 9
R23 | 4 | Overlapping module deadlines | Bottlenecks create merge/integration difficulties | Schedule (Project Management) | Poor sequencing | Merge conflicts | Mitigate: Stagger deadlines, use Gantt for schedule tracking | Athena | Likely | Moderate | Monitoring | 4 | 3 | 12
R24 | 4 | Missed lab submission deadlines | Overload or slippage leading to late submission | Schedule (Project Management) | Tight timeline | Last-minute work | Mitigate: Set internal deadlines earlier than official submission dates | Chloie | Possible | Major | Open | 3 | 4 | 12
R25 | 1 | Scope Creep | Uncontrolled scope growth mid-sprint | Scope Creep (Project Management) | Weak change control | Adhoc feature requests | Mitigate: Apply change request approval process | Quang | Likely | Major | Open | 4 | 4 | 16

## Risk Matrix
Probability/Impact | Negligible | Minor | Moderate | Major | Catastrophic
Rare
Unlikely |  | R06 | R13 | R05 | R14
Possible |  | R10 R19 | R02 R09 R12 R15 R18 R21 R22 | R07 R11 R24
Likely |  |  | R01 R04 R16 R17 R20 R23 | R03 R08 R25
Almost Certain

## Top 10 Risks
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R03 | 1 | Competitor apps | Platforms like PetBacker and Pawshake already exist with market share | Competitors (Business) | Strong existing competitors with more features and funding | Users trust and prefer existing apps | Mitigate: Focus on niche differentiation, local market focus | Chloie | Likely | Major | Open
R08 | 1 | Critical software bugs | Defects break major flows or data | Software (Technical) | Inadequate testing | Crashes or major bugs | Mitigate: Unit and integration tests, peer reviews, bug tracking | Zi Jian | Likely | Major | In Progress
R25 | 1 | Scope Creep | Uncontrolled scope growth mid-sprint | Scope Creep (Project Management) | Weak change control | Adhoc feature requests | Mitigate: Apply change request approval process | Quang | Likely | Major | Open
R01 | 4 | Low adoption due to poor usability | Users may not use the app if onboarding or navigation is confusing | Customer Adoption (Business) | Weak UI/UX design, no usability testing conducted | Drop-off during sign up, low retention | Mitigate: Conduct usability testing, simplify onboarding, gather feedback | Zi Jian | Likely | Moderate | Open
R04 | 4 | Limited budget for tools | Budget limits restrict paid APIs or hosting services needed for final delivery | Cash Flow (Business) | Insufficient funds | Blocked access to tools | Mitigate: Use open-source tools and student licenses | Quang | Likely | Moderate | Monitoring
R07 | 4 | Deployment environment failure | Hosting/misconfiguration will cause downtime near demo/submission | Hardware (Technical) | Misconfigured pipeline/host | Unavailable app | Mitigate: Conduct early deployment tests and maintain working backups | Anthony | Possible | Major | In Progress
R11 | 4 | API integration failure | Incorrect endpoints or API calls or data handling will cause errors between modules | Integration (Technical) | Mismatched interfaces | Broken screens | Mitigate: Conduct API integration tests with mock data | Quang | Possible | Major | Open
R16 | 4 | Lack of requirement validation | Wrong/partial features delivered/built in final product | User Support (Organizational) | Skipped validation | Rework and low satisfaction | Mitigate: Validate requirements with stakeholder during lab sessions | Athena | Likely | Moderate | Open
R17 | 4 | Imbalanced workload | Some members may be overloaded with work causing burnouts and delays in delivery | Team Support (Organizational) | Poor task allocation | Missed tasks | Mitigate: Track workloads, redistribute tasks accordingly | Chloie | Likely | Moderate | In Progress
R20 | 4 | Underestimation of effort | Tasks taking longer than planned | Estimates (Project Management) | Optimistic estimates | Sprint spillover | Mitigate: Re-estimate based on past sprints, add buffer for more critical tasks | Nelly | Likely | Moderate | Monitoring